Table 1	Overview table on planned timetable and planned assignments for GRULAC

All relevant information is be available at: http://www.unitar.org/cwm/global-monitoring-plan-pops-latin-american-and-caribbean-region

|  | Activity | Country / Actors | Dates / deadlines | Objective / Remarks |
| --- | --- | --- | --- | --- |
| 1 | Set-up the management structure for the project | UNEP BCCC/ SCRC |  | Agreement has been made |
| 2 | Organization of an inception workshop Prepare a detailed workplan for project implementation | BCCC/ SCRC | 2-4 December 2015 | Launch the GEF-funded project to continue regional support for the GMP in the GRULAC region and detail the activities and responsibilities of relevant stakeholders for project implementation with a workplan and budget |
| 3 | Agreements with countries | BCCC / SCRC, all countries | -By 8 December 2015: BCCC/SCRC to send reminder of information request and needs and a generic SSFA (modelo tipico-genérico) -By 15 January 2016: Countries to provide information to enable start with basic SSFA - By 15 February 2016: BCCC/SCRC to send draft SSFA -By 30 April 2016 (SSFA signed) | BCCC/SCRC to approach each country to determine terms of reference. Approach: First SSFA with basic information/commitments (around USD 80,000 /country) To amend as necessary |
| 4 | Assignment of responsible staff for air monitoring, mothers’ milk monitoring, and POPs analysis (including identification of national POPs lab) | Countries | Refer to specific document By 15 January 2015 (see point ii above) |  |
| 5 | Training needs Laboratory infrastructure / situation | UNITAR /Expert laboratories | -By 1st January 2016: BCCC/SCRC to send questionnaire with support of UNITAR & expert laboratories - By 15 February 2016: Countries to send questionnaire completed | Send questionnaire to update the database For planning purposes on training |
| 6 | Training of responsible personnel to establish and run the network for air samples and mothers’ milk sampling | CSIC | From June – December 2016 (2017?) A&B: late 2016 or early 2017 Argentina: 2016 Brazil: 2017 both Barbados: 2016 Colombia: 2017 Chile: 2016 Ecuador: late 2016 or early 2017 Jamaica: June-July 2016 Mexico: August 2016 Peru: early 2017 Uruguay: 2016 | At national level, no centrally organized training necessary; national experts aware of objectives of studies and procedures. The laboratory should be prepared/operational |
| 7 | Identification of sampling sites; type of sampler, existing number of PAS air samplers, number of samplers needed, number of resins needed (passive and active) | Countries UNITAR Expert laboratories BCCC/SCRC | -By 1 February 2016 : BCCC/SCRC to send check list of things to considers / conditions (e.g GIS, street, etc), including requirements for active sampler so that the selection of the site to place it can be defined. -By 1 March 2016: Countries to provide information -From 1 May 2016 Samplers and PUF to be send by CSIC - Sampling starts 1 July 2016 |  |
| 8 | Identification of potential donors of mothers’ milk in the 6 countries |  | -By 1 February 2016 Expert laboratory & BCCC/SCRC to send check list of things to considers / conditions , ethical clearance / conditions, etc Countries to initiate process to get ethical clearance as soon as possible to enable start of sampling by 1 January 2017 Cut off day for sample reception will be defined with the expert laboratory and notified accordingly |  |
| 9 | Participation in international intercalibration study | IVM/MTM | PERIOD: 2016-2018 -By 29 February 2016 /2018: Invitation/confirmation to labs to participate -By 1 April 2016 / 2018: registration open -By 15 May 2016 / 2018: Samples to be sent to participating labs -By 31 July 2016 / 2018: Results reported by participating labs | Invitation/confirmation to labs participating at intercalibration study : 29 February 2016 / 2018 Registration until: 1 April 2016/ 2018 Samples to be sent by: 15 May 2016 / 2018 Results reported by labs until: 31 July 2016 / 2018 |
| 10 | Collection of national air samples and preparation of pools where applicable |  | From October 2016 and thereafter every 3 months (to be confirmed) |  |
|  | Collection mothers’ milk samples and preparation of pools where applicable |  |  | Send to WHO Reference lab/Freiburg until Analysis |
| 11 | Exchange of national samples for POPs analysis in developing country laboratory and mirror analysis in back-up laboratory |  | 2017 or after |  |
| 12 | Evaluation of analytical data and interpretation of results | MTM, IVM, CSIC |  | Expert labs will contact developing country labs and exchange results |